## Slide 1
Kick-Off meeting
SMATH Project
Venice – June 15th 2018
Imane Madi –Project officer Interreg MED Joint Secretariat

## Slide 2
1. Reporting procedure: overview
2. Project progress report
3. First Level Control system
4. Declaration of expenditure
FLC system and
Reporting procedures

## Slide 3
Reporting deadline every 6 months according to the timetable included in art. 5 of the Subsidy Contract
Rules aligned to the EU Regulations with the overall objective of shortening the pre-financing period
The payment claim should be signed and stamped by the legal representative of the LP and sent to the JS (original version)
Reporting procedure

## Slide 4
Progress Report and Payment claim must be submitted to the JS within 3 months after the end of each implementation period (NO delays accepted)
Eligibility of expenditure starts 16/01/2018
End of the last period corresponds to the end of the project: submission within 3 months from project end
Implementation Period | Submission date
01/02/2018-31/08/2018 | 30/11/2018
01/09/2018-28/02/2019 | 31/05/2019
01/03/2019-31/08/2019 | 30/11/2019
01/09/2019-29/02/2020 | 31/05/2020
01/03/2020-31/08/2020 | 30/11/2020
01/09/2020-28/02/2021 | 31/05/2021
01/03/2021-31/08/2021 | 30/11/2021
01/09/2021-31/01/2022 | 30/04/2022
Reporting procedure - Timing
Notes: Fin de la première periode de mise en œuvre 30/08/2018
3 mois pour certifiés : 30/11/18 (payment claim submission deadline

## Slide 5
LP fills out a project progress report
Each partner fills in a progress report
LP collects information on activities and deliverables
Deliverables are uploaded on the Web-Platform
LP collects FLC certificates and validates a payment claim (ERDF and IPA)
All partners enter expenditure
LP validates partners’ expenditure
Expenditure certification by the FLC
Project progress report and Payment claim submitted by the LP to the JS on time!!!
Content reporting
Financial reporting – declaration of expenditure
Reporting procedure - Overall
COORDINATION PP – LP – FLC

## Slide 6: Project progress report

## Slide 7
Quality of reporting:
Avoid a “partner per partner approach” (no copy paste from partner reports!) > Well harmonised and exhaustive report
In the section Highlights of main achievements clearly summarise what has been achieved during the 6 months of implementation
Include the «good practices» and any difficulties faced during project implementation.
Project progress report

## Slide 8
Pay attention to the format of the deliverable to be uploaded:
If possible, upload the deliverable in its original format
All deliverables should be developed in a format freely accessible for use and reuse, ideally in an open source format
If not possible to upload in original format (e.g. because the deliverable is an event or a complex production) upload a detailed report on the activity
All deliverables must respect the project branding and publicity rules!!
Project progress report

## Slide 9: Declaration of expenditure and First Level Control system

## Slide 10
The reporting of expenditure has to be done for each individual cost. One invoice corresponds to one expenditure.
No upload of expenditures documents on Synergie CTE
Amounts should be reported with or without VAT depending on the VAT status of the partner declared in the Application Form
The expenditures can be entered on Synergie CTE throughout the whole implementation period… DO NOT WAIT UNTIL LAST MINUTE!!!
Set a planning with your FLC
More information in Synergie guide: “How to enter an expenditure”
Declaration of expenditure
Notes: The reporting of expenditure has to be done for each individual cost. One invoice corresponds to one expenditure. (In cases where there are no invoices e.g. public transport tickets, costs can be grouped as one expenditure item (if they relate to the same Budget Line and same Wok Package). In the case of staff costs, an expenditure should be included by staff member, month and WP.)

## Slide 11: Lead Partner validation
First step of the validation process  “Expenditure in validation process” by the Lead partner
No eligibility check
Verification of the conformity of the expenditure against the activities foreseen in the application form and effectively done by the partner in the framework of the project
After they will appear as “expenditure submitted to the FLC for certification” in Synergie CTE
More information in Synergie guide: “How to validate an expenditure as LP”
Notes: First reporting deadline in autumn 2017
1st period will cover till 30/06/17
Summer for certification
Progress Report will have to be prepared for September 2017
> Please remember that reporting on Synergie CTE + Web platform + exchanges with JS are foreseen

## Slide 12: First Level Control definition
National Control Systems
Responsible for verifying that the expenditure declared by beneficiaries complies with the applicable law and the Programme rules  Article 23 (4) of Regulation (EU) No 1299/2013
FLC Covers 100% of all declared expenses
Administrative verifications every six months
On-the-spot checks at least once during the project lifetime
A guarantee for beneficiaries that project accounts comply with the legal and financial provisions of the Subsidy Contract, the Interreg MED Programme rules and EU and national provisions

## Slide 13: National control systems
Each Member State
  Has set up a First Level Control system
  Has determined the selection mode for controllers
Each partner:
  Must refer to the control system of the State where it is located
  Must follow the information provided by the national bodies on the selection procedure
  Centralised systems: Croatia, Greece, Slovenia, UK (Gibraltar), Albania, Bosnia and Herzegovina, Montenegro
  Decentralised systems: Cyprus, France, Italy, Malta, Spain and Portugal

## Slide 14: Controller designation process
Centralised:
Contact the national FLC to be informed of procedure to be followed for the submission of the expenditure
Decentralised:
Contact the NCP to be informed of the procedure to follow for the selection and approval of your FLC
Select your FLC (internal-external) and submit it for the approval of your NCP
Once it is approved, request in Synergie CTE and access for your FLC
Once the request is validated by the NCP, the FLC will have access to Synergie CTE
To be done as soon as possible, so you can certify expenditure!!!!!
Notes: Selection and approval of the FLC:
In centralised system, nothing to be done by partners
In decentralised systems, selection of the FLC to be done by partners as soon as possible
>>> Once the selection of the FLC is approved by partner’s National Authority, information should be included in Synergie so FLC access can be granted.
For more information, see relevant Synergie guide.

## Slide 15: First Level Control
Reality of the declared expenditure and Delivery of the products and services co-financed (as stated in the AF)
Soundness of the declared expenditure
Eligibility rules and conditions for support of the project and payment
Existence of an adequate audit trail
Existence of an accounting system and mechanism(s) to avoid double funding
Each six months FLC must :
Control partner expenditure
Certify partner expenditure
Validate in Synergie CTE the FLC certificate
      official commitment
      the control checklist
      list of verified expenditure
Print, sign and stamp the FLC certificate
To be uploaded by partner on Synergie
Notes: Each six months FLC must :
Verify partner expenditures;
Validate the partner expenditures
Fill-in the FLC checklist in SYNERGIE CTE
Validate in SYNERGIE CTE the FLC certificate
    official commitment on validation of expenditures,
    the control checklist
    list of verified expenditure
Print, sign and stamp the FLC certificate in order to be included in the partner audit trail.
Deadlines for project reporting set up in the Subsidy Contract
Delays impede constant cash-flow and have a negative impact on financial performance of the projects and the Programme

## Slide 16: Expenditure reporting procedure
1 | Each partner enters activities and expenditure on Synergie CTE | PP
2 | Lead Partner validates the partners’ expenses on Synergie CTE | LP
3 | FLC of each partner (centralised or decentralised system) | FLC/PP
 | Validates the eligible expenditure | 
 | Generates a FLC certificate on Synergie CTE | 
4 | In Spain and Portugal: FLC certificate is validated by the responsible National Authority | NA/FLC/PP
5 | Lead Partner checks that all certificates are uploaded and produces a payment claim on Synergie CTE | LP
Notes: 16

## Slide 17
Each partner
Lead Partner
Managing Authority & Joint Secretariat
Certifying Authority
Lead Partner
First Level Control
Enter expenditure and partner progress report
Validate partners expenditure
Control of expenditure and FLC certificate
Submit project progress report and Payment claim;
Upload deliverables in webplatform
MA/JS checks
CA checks
Payment to each partner
Reporting procedure
Notes: Each partner: Enters activities and expenditures on SYNERGIE CTE
Lead Partner: Validates the other partners’ expenses on SYNERGIE CTE
First Level Control: Checks partner expenditures-Validates the partner expenditures and fill-in the FLC checklist in SYNERGIE CTE-Validates in SYNERGIE CTE the FLC certificate
National Level: In some Participating States*, the expenditures certified by FLC must be validated at national level before their inclusion in a project payment claim.
Lead Partner: Gathers all the certificates and produce a payment claim + progress report on SYNERGIE CTE - Submits to the JS within the deadlines mentioned in the Subsidy Contract
Joint Secretariat: Verifies the project’s payment claim, address the LP in case of doubts - Prepares the MA certificate
Managing Authority: Performs an additional control and ensures the precision of the payment claim - Validates the MA certificate - Transfers the MA certificate to the Certifying Authority
Certifying Authority: Performs an additional control - Draws up payment order directly to each beneficiary

## Slide 18: Reporting timing
End of the 1st implementation period: 30/08/2018
Payment claim submission deadline: 30/11/2018
Start-up of the Project: 01/02/2018
Validation of the MA: 4/5 months
Payment to the partner
Approval of projects: 16/01/2018
Expenditures paid out from 16/01/2018 to 30/08/2018
FLC selection & approval
Establishment audit trail
Certification of expenditures by FLC
&
Progress Report by LP
Treatment by JS & Answer to requests of clarifications
Confirmation reimbursement by partners
COORDINATION PP – LP – FLC

## Slide 19
Thank you !