## Slide 1
Speakers: Valeria Stacchini – finance project manager
Partner: LP – Metropolitan City of Bologna
web kick-off meeting | 22 – 23 April 2020
23th April 2020
Project Management

## Slide 2
Main Points
Start-up activities
Simple PM chart
Risk management plan
Reporting
Q&A

## Slide 3
Start-up activities

## Slide 4
Signed on 31.03.20
Subsidy contract
In time on all deliversables
Task M.1: Start- up activities
available on Metrocloud
GANTT updated

## Slide 5
In time on all deliversables
Task M.1: Start- up activities
Deadline: 2 months from the SC then by 31.05
Status:
M.1.1: Partnership agreement
Deadline: April
Status:
M.1.2: Simple PM chart
Deadline: April
Status:
M.1.3: Kick-off meeting
Deadline: May
Status:
M.1.4: Other Startup requirements
Deadline: May
Status:
M.1.5: Risk Management plan

## Slide 6
project stamp needed
always check minimum information needed on finance documents
eMS – assignment of specific user(s)
Information on the location of the official documents
FLC information: please get in touch with your National Contact point to receive information.
Next steps
Pro-memoria from yeasterday JS presentation

## Slide 7
What we need to get the money:
PA signed
reports must be certified by FLC (even if it is a slump-sum)
We suggest to claim preparation costs with PR01
Preparation costs
Pro-memoria from yeasterday JS presentation

## Slide 8
10% of the IPA II contribution – only for IPA partners
What we need to get the money:
Automatically, after the signature of the Partnership Agreement;
To be compensated in equal shares with the first two payments requested by the IPA partners.
Process: JS – LP – IPA pps
IPA pre-financing
Pro-memoria from yeasterday JS presentation

## Slide 9
01
02
04
06
08
2
MCBO
04.2020
03
05
07
PG meetings
SEBS
07.2020
PSP
11.2020
UIRS
02.2021
RDCN
06.2021
DUNEA
11.2021
AUEB
04.2022
RFVG
08.2022
SC
SC
SC
SC
Transnational seminars,
workshops, study visits
Mid-term event
Dialogue on CreaTourES pathway
Final event
ADRION General States of Culture&Tourism
+2 Set.
+1 Dec.
On-line PG at the end of June – begin of July.

## Slide 10
Approved budget and spending plans must be carefully respected
projects underspending may result in programme lack of financial performance and consequent de-commitment of unspent funds from the European Commission (“N+3 rule”).
DE-COMMITMENT RISK
Partners who did not spend all their budget in the 1st period should:
explain the reasons in their partner report.
Justifications should be also included in the progress project report.
Partners have the possibility to spend the unspent amount in the next reporting period. However, in case of de-commitment at Programme level, the project budget could be proportionally reduced.

## Slide 11: Planned Budget per period 0&1 / per partner

## Slide 12
Monitoring the level of expenses
Starting public procurement on time
Cooperating with External Expertise
Keeping good records!!
…do not mind to ask if you have any doubt!
Reporting - Focus on

## Slide 13
Main Points
Start-up activities
Simple PM chart
Risk management plan
Reporting
Q&A